## Backlog
Weighted Shortest Job First WSJF Formula |  |  |  |  | Estimate in Fibonacci Range: 0, 1, 2, 3, 5, 8, 13, 21.
Calibrate what is 1 and 21 for your team.
Spreadsheet developed by dionatanmoura.com |  |  |  |  | WSJF is developed by scaledagileframework.com
Weighted Shortest Job First Prioritization
User-Business Value | Time Criticality | Risk Reduction - Opportunity Enablement | Job Duration | WSJF Priority | Product Backlog Items | Category
13 | 5 | 5 | 1 | 23 | Example 7 | Feature
1 | 1 | 1 | 1 | 3 | Example 4 | Bug
1 | 21 | 1 | 8 | 2.875 | Example 5 | Enabler
21 | 3 | 21 | 21 | 2.1429 | Example 1 | Epic
13 | 2 | 8 | 13 | 1.7692 | Example 6 | Feature
0 | 1 | 1 | 2 | 1 | Example 2 | Technical Debt
1 | 1 | 1 | 3 | 1 | Example 3 | User Story
0 | 0 | 1 | 1 | 1 | Example 8 | Technical Debt
0 | 0 | 0 | 0 | 0 |  | Select...
0 | 0 | 0 | 0 | 0 |  | Select...
0 | 0 | 0 | 0 | 0 |  | Select...
0 | 0 | 0 | 0 | 0 |  | Select...
0 | 0 | 0 | 0 | 0 |  | Select...
0 | 0 | 0 | 0 | 0 |  | Select...

## Estimates
0
1
2
3
5
8
13
21

## Categories
Select...
Epic
Feature
User Story
Technical Debt
Bug
Enabler